## Sheet1
| PROJECT TITLE | Smart Auto Gate Using Plate
| PROJECT MANAGER | Jasni Jazali Bin Mohd Zamri (B031910077)
| PROJECT MEMBERS | Wan Ali Bin Mohamad Pauzi (B031910397) |  |  | Farabi Tasnim Ahmed (B031910397) | Mukheish Rao A/L M.Apparao (B031910397)
| COMPANY NAME | casaIoT
| DATE | 2021-11-07
| GitHub | https://github.com/openoneforme/AutoGatePlateRecognition
Surveyor casaIoT Project Cost Estimate
|  | # Units/Hrs. | Cost/Unit/Hrs. | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1 | Project Management |  |  |  | $200000 | 20%
1.1 | Project manager | 850 | $100 | $85000
1.2 | Project team members | 1560 | $65 | $101000
1.3 | Contractors (10% of software development and testing) |  |  | $14000
2 | Hardware |  |  |  | $85000 | 8.5%
2.1 | Handheld | 100 | $800 | $80000
2.2 | Servers | 1 | $5000 | $5000
3 | Software |  |  |  | $350000 | 35%
3.1 | Licensed software | 100 | $250 | $25000
3.2 | Software development |  |  | $325000
4 | Testing (10% of total hardware and software costs) |  |  | $40000 | $40000 | 4%
5 | Training and Support |  |  |  | $150000 | 15%
5.1 | Trainee cost | 100 | $400 | $40000
5.2 | Travel cost | 15 | $600 | $9000
5.3 | Project team members | 1560 | $65 | $101000
6 | Reserves (20% of total estimate) |  |  |  | $175000 | 17%
| Total project cost estimate |  |  |  | $1000000
Surveyor casaIoT Software Development Estimate
1 | Labor Estimate | # Units/Hrs. | Cost/Unit/Hrs. | Subtotals | Calculations
| Contractor labor estimate | 2500 | 125 | 312500 | 2500*125
| Project team member estimate | 1560 | 65 | 101400 | 1560*65
| Total labor estimate |  |  | 413900 | Sum above two values
2 | Function point estimate** | Quantity | Coversion Factor | Function Points | Calculations
| External inputs | 15 | 3 | 45 | 15*3
| External interface files | 5 | 5 | 25 | 5*5
| External outputs | 7 | 8 | 56 | 7*8
| External queries | 3 | 1 | 3 | 3*1
| Logical internal tables | 2 | 3 | 6 | 2*3
| Total function points |  |  | 135 | Sum above funtion point values
| Assumed value from reference |  |  | 32 | Assumed value from reference
| Source lines of code (SLOC) estimate |  |  | 4320 | 135*32
| Productivity*KSLOC^Penalty (in months) |  |  | 14.495 | 3.13*4.32*1.072
| Total labor hours(160 hours/month) |  |  | 2319.2 | 14.495*160
| Cost/labor hour ($120/hours) |  |  | 120 | Assumed value from budget expert
| Total function points estimate |  |  | 278304 | 2319.2*120